## Follow-up
[7 empty] | DEVELOPMENT | [5 empty] | Testing |  |  |  | DEPLOYMENT
S.No | Application | Object name / Requirement description | System | Object type | AS - IS and mpact of MS deactivation on Dec 03rd | TO- BE | Efforts ( in MD) | Change Document | Transport request | Target delivery date | Status | Comments | Status in DEV | Status in INT | Status in Pre-Prod | Sanity checks in Pre-Prod with PYDOC | Documentation changes SD, test dossier) | KT session to AI and DOPC | myPortfolio update | Demo to PYDOC | Target MiP | Synchronisation with Project team - Infosys | Test Folder | https://drive.google.com/drive/folders/1S2cmxmhqxqhJ5aTNN2DVyDuTKjeAC1yJ
[7 empty] | Doer : Ramesh |  |  | Doer : Ramesh | Doer : Ramesh |  | Doer : Ramesh | Doer : Gwen/Benoit | Doer : Gwen/Benoit |  | Doer : Ramesh | Doer : Ramesh and Karthik | Doer : Elsa | Doer : Ruchika /Gwen
1 | SAP | ZPMDBR_WPFIS_MASS_QIR_UPDATE | DEM | Report program | Excel file, no workaound possible | AS IS: real excel file used to run program | 3 | 152048 | DEMK931402 | 2024-11-27 | Done | in scope = Received template and WIP. | Done | Done | Not started | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
2 | SAP | ZPMQMB_NPI_QIR_REGISTER_INIT | DEM | Report program | csv file | out of scope for MS Decom |  |  |  |  | N/A | Not in scope, not used anymore | N/A | N/A | Not started |  |  | N/A | by mid Feb
3 | SAP | ZPMQMB_NPI_QIR_REGISTER_BUGFIX | DEM | Report program | csv file | out of scope for MS Decom |  |  |  |  | N/A | Not in scope, not used anymore | N/A | N/A | Not started |  |  | N/A | by mid Feb
4 | SAP | ZPMQMB_WPF_QIR_INIT | DEM | Report program | csv file | out of scope for MS Decom |  |  |  |  | N/A | Not in scope, not used anymore | N/A | N/A | Not started |  |  | N/A | by mid Feb
5 | SAP | ZPMDBR_WPFIS_MASS_QIR_UPD_GBL | DEM | Report program | csv file | out of scope for MS Decom |  |  |  |  | N/A | Not in scope, not used anymore | N/A | N/A | Not started |  |  | N/A | by mid Feb
6 | SAP | Transaction ZFNAMASS / Program - ZPMDBT_FNA_MASS_CREATE | DEM | Report program | csv file | Upload functionality for 3 scenarios = Standard = Derived = Specified | 5 | 152048 | DEMK931402 | 2024-11-04 | Done | Changes are available in DEM -26/11 - changes documented | Done | In progress | Not started | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | GB : Issue with GSheet. Same as in DEM first (looping in the autorisation process) 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
7 | NSPI | NSPI Manage QFolder | DFE | UI5 Application |  | Z_I740_QFOLD_MA |  |  |  |  | N/A | No Export option | N/A | N/A | Not started | Week 05 | Not started | Not started | by mid Feb |  |  | GB : Credentials requested for GSheet access
| NSPI | NSPI Manage QIR | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | z_i740_sin_reg | 3 | 151938 | DFEK962733 | 2024-12-02 | Done | New due date for dev & Testing until Pre-prod : Jan 15th | Done | Done | Done | Week 05 | Done |  | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
8 | NSPI | NSPI --> Manage Material Request | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_i740_mat_mng | 3 | 151938 | DFEK962733 | 2024-12-05 | Done | New due date for dev & Testing until Pre-prod : Jan 15th | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
9 | AQPL | AQPL => AQPL | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | add both xlsx and gdrive Z_I740_AQPL | 3 | 151938 | DFEK962733 | 2024-12-10 | Done | Keep both XLSX and GDrive | Done | N/A | Not started | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
10 | AQPL | AQPL => Interchangeability | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | add both xlsx and gdrive z_i740_icy | 3 | 151938 | DFEK962733 | 2024-12-13 | Done | Keep both XLSX and GDrive | Done | N/A | Not started | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
11 | myComp | myComp => Manage CFolder | DEA | UI5 Application | Excel file, but workaround OK for extracting from tool | z2f81_wpfis Download gsheet implementation | 3 | 151938 | DFEK962733 | 2024-11-25 | Done | New due date for dev & Testing until Pre-prod : Jan 09th | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done before C21 scope (dev team)
12 | myComp | myComp => Manage QIR | DEA | UI5 Application | Excel file, but workaround OK for extracting from tool | z2f81_wpfis Download gsheet implementation | 2 | 151938 | DFEK962733 | 2024-11-20 | Done | New due date for dev & Testing until Pre-prod : Jan 09th | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done before C21 scope (dev team)
13 | myComp | myComp => T2DD | DEA | UI5 Application | Excel file, but workaround OK for extracting from tool | z2f81_wpfis Download gsheet implementation | 2 | 151938 | DFEK962733 | 2024-11-20 | Done | New due date for dev & Testing until Pre-prod : Jan 09th | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done before C21 scope (dev team)
14 | myCSL | myCSL => Manage SIR (OLW) | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | All 3 icon toolbar =Procurement Operations A/C related Services =Procurement General Services =Procurement Operations Out Located Work Z_2T65_CSL_SIR | 4 | 154490 | DFEK964607 | 2025-01-20 | Done | Dev conflict C21 => coordination with Infosys to be done for MIP dates | Done | Done | Not started | Week 05 |  | Not started | by mid Feb | Jan 28th | Feb 12th | Post 10th Jan - Dev to start 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
15 | myCSL | myCSL => Manage WS | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | z_2t65_csl_ws | 3 | 154490 | DFEK964607 | 2025-01-23 | Done | Dev conflict C21 => coordination with Infosys to be done for MIP dates | Done | Done | Not started | Week 05 |  | Not started | by mid Feb | Jan 28th | Feb 12th | Post 10th Jan - Dev to start 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
| myCSL | Search Service & Contact | DFE | UI5 Application |  | z_2t65_cslv3ssc | 3 | 154490 | DFEK964607 | 2025-01-28 | Done |  | Done | Done |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
| myCSL | Manage WS line | DFE | UI5 Application |  | z_2t65_cslv3mws | 3 | 154490 | DFEK964607 | 2025-01-31 | Done |  | Done | Done |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
| myCSL | Display SIRs | DFE | UI5 Application |  | Z_2T65_CSL_DIS | 3 | 154490 | DFEK964607 | 2025-02-05 | Done |  | Done | Done |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th | 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
16 | myQSPL | myQSPL => Request | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_FD45_QSPL_REQ | 3 | 151938 | DFEK962733 | 2024-12-18 | Done | MiP conflicts with Project => alignement meeting to be done | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
17 | myQSPL | myQSPL =>Qualification | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_FD45_QSPL_QUA | 3 | 151938 | DFEK962733 | 2024-12-23 | Done | MiP conflicts with Project => alignement meeting to be done | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
18 | myQSPL | myQSPL => Generate Report (NB: despite its name, the option 'xls' generates an xlsx) | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | ZFD45_QSPL_GR | 4 | 151938 | DFEK962733 | 2025-01-02 | Done | MiP conflicts with Project => alignement meeting to be done Development completed except - dynamic labels & Disclaimer tab | Done | Done | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
19 | myQTML | myQTML => Manage Request | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_3F9F_QTML_MR | 2 | 151938 | DFEK962733 | 2025-01-06 | Done | MiP conflicts with Project => alignement meeting to be done | Done | Not started | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
20 | myQTML | myQTML => Manage Qualif | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_3F9F_QTML_MQ | 2 | 151938 | DFEK962733 | 2025-01-08 | Done | MiP conflicts with Project => alignement meeting to be done | Done | Not started | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
21 | myQTML | myQTML => Generate Report (NB: despite its name, the option 'xls' generates an xlsx) | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | Z_3F9F_QTML_GR | 3 | 151938 | DFEK962733 | 2025-01-13 | Done | MiP conflicts with Project => alignement meeting to be done Development completed except - dynamic labels & Disclaimer tab | Done | Not started | Done | Week 05 | Done | Not started | by mid Feb | Jan 28th | Feb 12th | Waiting for BUS GO to freeze V2.2 solution before starting MS decom dev - Doer Gaurav 15/01: MiP MS decom to be done Feb 12th with C21 MiP or after.
| All | Harmonise name of new button into "Export to G Drive" | DFE | UI5 Application |  |  | 1 |  |  | W3 | Done | Free text to be added. Final inputs from PYDOC provided on Jan 06th Go for starting dev. | Done | Done |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th
| All | Name of G-sheets on Google drive including application name and date - after export | DFE | UI5 Application |  |  | 1 |  |  | W3 | Done | - File name including application name : refer to current names used via Excel => to be checked with Gaurav + Wait final inputs from PYDOC - Timestamp to be added Final inputs from PYDOC provided on Jan 06th Go for starting dev. | Done | Done |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th
| AQPL | For external users (to keep possibility to use Excel) | DFE | UI5 Application |  |  | 1 |  |  | 10 Feb 25 - to be revised | Done | Have 2 specific buttons : - 1 for Excel (deactivated for internal access) - and 1 for G Drive. Next steps: Design to be defined with Ramesh/ Gwen (distinguishing uses cases) |  |  |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th
| myQSPL & myQTML | Check if impact on Automatic upload to partner portal | DFE | UI5 Application | [6 empty] | In progress | Doer: Gwen/Benoit with Gaurav + Laura Del Alamo Actions: - check current solution with Gaurav => Done , file generated not linked to Excel. NOt blocking for MS decom - Laura to check compatilibilty with SNS decommissioning |  |  |  | Week 05 |  |  | by mid Feb | Jan 28th | Feb 12th
21 | AQPL & NSPI | Impact on files due to G- sheet restriction to 10 M cells | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | No development to do. Keep current process for boyth, waiting for approval from Anna |  |  |  |  | In progress | Doer: Gwen/Benoit for testing Tests for AQPL & NSPI files : until file opening. Results of tests: - AQPL : solution to open the gsheet file => using Notepad - NSPI : KO => after analysis with Anna: proposal to be checked => reduce the period of data inside the file. 23/01: to get final view from Aana | N/A | N/A | N/A | Week 05 |  | Not started | by mid Feb | Jan 28th | Feb 12th
21 | All | Possibility to have automatic tagging of G-sheets on Google drive | DFE | UI5 Application | Excel file, but workaround OK for extracting from tool | [5 empty] | Done | Not allowed by Airbus Security. Doer: Gwen/Benoit to provide Airbus documentation / golden rules on security to justify the rejection. Alternative way : create a folder with configured tagging => apply rules for all documents located in this folder https://airbus.service-now.com/esc?id=sc_cat_item&table=sc_cat_item&sys_id=94858fa01becc2503a95ed30604bcb5c&searchTerm=automate%20tagging | N/A | N/A | N/A | N/A | Not started | N/A | by mid Feb | Jan 28th | Feb 12th
ISSUES TRACKER
| Date | Topic |  |  |  | Action - Resolution | Efforts ( in MD) | Status | Comments | Workaround
| 20/12 | On actual reports: - with Excel : there is a disclaimer + a tab for data - with Gsheet : only 1 tab possible |  |  |  | - Ramesh to check workaroud to propose? => possbility to merge disclaimer into data tab? - Gwen To contact MS Decom team | 7 | Done | Technical analysis POC program creation Development Testing documentation 23/01: solution exists for XEA, to be implemented for XEM. action in progress by Ramesh. Solution to deliver in INT > mid week 05 Test DOPC > by end week 05 BUS test week 06 (1 week delay) Target MiP Feb 12th | 1. Disclaimer to add in application below the Generate button. 2. Disclaimer popup to show on Generate Report button with Agree checkbox, Export GDrive and Cancel buttons. 3. Checking if any other solution to meet our requirement. ZDEMO_EXCEL22, ZDEMO_EXCEL23 refer in DEA | DEMK931960 152048, [Qualif] MS Decom xEM DFEK964946 151938, [Qualif] MS Decom - XFE
| 20/12 | myQTML Report : - AS IS : some colomns contain years (2023, 2024,2025 et 2026) corresponding to Year -1, Year, Year+1,... => using dynamic labells - TO BE: with Gsheet no possiblity to use dynamic labells field |  |  |  | - Ramesh checked the workaround > no solution - Gwen To contact MS Decom team | 7 | Done | Technical analysis POC program creation Development Testing documentation 23/01: solution exists for XEA, to be implemented for XEM. action in progress by Ramesh. Solution to deliver in INT > mid week 05 Test DOPC > by end week 05 BUS test week 06 (1 week delay) Target MiP Feb 12th | NO ZDEMO_EXCEL22, ZDEMO_EXCEL23 refer in DEA | DEMK931960 152048, [Qualif] MS Decom xEM DFEK964946 151938, [Qualif] MS Decom - XFE
| 20/01 | QTML/ QSPL Generate reports application: the XLS option in the report was in the 1st place, and now the Gsuite option is at the end |  |  |  | - Ramesh to do the changes |  | Done
| 20/01 | QTML/ QSPL Generate reports application: change the name of that to "GSheet" instead of My Drive (as it's a format ) |  |  |  | - Ramesh to do the changes |  | Done
| 20/01 | File name changes if any in all the UI5 Applications |  |  |  | - Gwen to check with Business and confirm - Ramesh to do the changes |  | N/A
| 28/01 | NSPI - Export to my drive throws error with huge volume of data 414 URI Too long | [5 empty] | Done | Issue identified and fixed.

## Label names
UI5 app name | System | Application type | Details | Current button name | New button name | Current file name | New File name | Name Validated ?
NSPI QFolder => Manage QIR / | DFE | UI5 Application | z_i740_sin_reg | Download GSheet | Export to My Drive | ETListSet | NSPI_Qualif_export_<Timestamp> | Yes | NSPI_Qualif_export_08012025_160129
NSPI - material_manage | DFE | UI5 Application | Z_i740_mat_mng | Export GSheet | Export to My Drive | NSPI_Request_export_07012025 | NSPI_Request_export_<Timestamp> | Yes | NSPI_Request_export_08012025_160753
AQPL => AQPL | DFE | UI5 Application | Z_I740_AQPL | 1. Export GDrive Technical Note 2. Export GDrive AQPL Data 2.a --> My current QPL results 2.b --> GE QPL 2.c --> UK, FR, SP QPL 3. Export Technical Note 4. Export AQPL Data 4.a --> My current QPL results 4.b --> GE QPL 4.c --> UK. FR, SP QPL | 1. Export to my Drive Technical Note 2. Export to my Drive AQPL Data 2.a --> My current QPL results 2.b --> GE QPL 2.c --> UK, FR, SP QPL | 1. TN_List_07012025 2.a --> Customized_Export_07012025 2.b --> GE_QPL_07012025 2.c --> UK_FR_SP_QPL_07012025 3. TN_List_07012025 4.a --> Customized_Export_07012025_224736 4.b --> GE_QPL_07012025 4.c --> UK_FR_SP_QPL_07012025 | 1. TN_List_07012025 2.a --> Customized_Export_07012025 2.b --> GE_QPL_07012025 2.c --> UK_FR_SP_QPL_07012025 3. TN_List_07012025 4.a --> Customized_Export_07012025_224736 4.b --> GE_QPL_07012025 4.c --> UK_FR_SP_QPL_07012025 | No | TN_List_08012025_162512 Customized_Export_08012025_162548
AQPL => Interchangeability | DFE | UI5 Application | Z_I740_ICY | 1. Export 2. Export GDrive | Export to My Drive | 1. ICY_Export_07012025_225057 2. ICY_Export_07012025_225101 | 1. ICY_Export_07012025_225057 2. ICY_Export_07012025_225101 | No
myComp => Manage QIR | DFE | UI5 Application | z2f81_wpfis | Download GSheet | Export to My Drive | et_qirSet | myComp_qualif_export_<Timestamp> | Yes | myComp_qualif_export_08012025_181855
myComp => Manage CFolder | DFE | UI5 Application | z2f81_wpfis | Download GSheet | Export to My Drive | ET_CFOLDERSet | myComp_Cfolder_export_<Timestamp> | Yes | myComp_Cfolder_export_08012025_182342
myComp => T2DD | DFE | UI5 Application | z2f81_wpfis | Download GSheet | Export to My Drive | ETT2ddSet | myComp_T2DD_export_<Timestamp> | Yes | myComp_T2DD_export_08012025_182713
myCSL => Manage SIR | DFE | UI5 Application | z_2t65_csl_sir |  | Export to My Drive | DisplaySIRs_export_08012025 | SIRs_export_<Timestamp> | Yes
myCSL => Manage WS | DFE | UI5 Application | z_2t65_csl_ws |  | Export to My Drive | export (18) | WS_export_<TimeStamp>.xlsx | Yes
myCSL => Manage work specification line | DFE | UI5 Application | z_2t65_cslv3mws |  | Export to My Drive | WS_line_export_08012025 | WS_line_export_<Timestamp> | Yes
myCSL=> Display SIR | DFE | UI5 Application | Z_2T65_CSL_DIS | Download GSheet | Export to My Drive | DisplaySIRs_export_08012025 (1) | DisplaySIRs_export_<Timestamp>.xlsx | Yes
myCSL=> Search Service & Contact | DFE | UI5 Application | z_2t65_cslv3ssc |  | Export to My Drive | CSLV3_export_08012025_081503 | CSLV3_export_<Timestamp> | Yes
myQSPL => Manage Request | DFE | UI5 Application | Z_FD45_QSPL_REQ | Export to GDrive | Export to My Drive | MyQSPL_exportrequest_07012025_230125 | MyQSPL_exportrequest_<Timestamp> | Yes
myQSPL => Manage Qualif | DFE | UI5 Application | Z_FD45_QSPL_QUA | Export to GDrive | Export to My Drive | MyQSPL_export_07012025_230406 | MyQSPL_export_<Timestamp> | Yes
myQSPL => Generate Report (NB: despite its name, the option 'xls' generates an xlsx) | DFE | UI5 Application | ZFD45_QSPL_GR | GDrive <Radio button> | My Drive | 1. MyQSPL_LqaDashboard_07012025_230455 2. EXTERNAL_IN_07/01/2025 3. EXTERNAL_EX_07/01/2025 4. QSPL_INTERNAL_07/01/2025 | 1. MyQSPL_LqaDashboard_07012025_230455 2. EXTERNAL_IN_07/01/2025 3. EXTERNAL_EX_07/01/2025 4. QSPL_INTERNAL_07/01/2025 | No
myQTML => Manage Request | DFE | UI5 Application | Z_3F9F_QTML_MR | Export to GDrive | Export to My Drive | MyQTML_exportrequest_07012025_232058 | MyQTML_exportrequest_<Timestamp> | Yes
myQTML => Manage Qualif | DFE | UI5 Application | Z_3F9F_QTML_MQ | Export to GDrive | Export to My Drive | MyQTML_exportqualif_07012025_232226 | MyQTML_exportqualif_<Timestamp> | Yes
myQTML => Generate Report (NB: despite its name, the option 'xls' generates an xlsx) | DFE | UI5 Application | Z_3F9F_QTML_GR | GDrive <Radio button> | My Drive | 1. PTP_Kit_07_01_2025 2. External_report_independent_07_01_2025 3. External_report_captive_07_01_2025 4. QTML_Internal_report_07_01_2025_23_28_53 | 1. PTP_Kit_07_01_2025 2. External_report_independent_07_01_2025 3. External_report_captive_07_01_2025 4. QTML_Internal_report_07_01_2025_23_28_53 | No
ZPMDBR_WPFIS_MASS_QIR_UPDATE |  |  | ZPMDBR_WPFIS_MASS_QIR_UPDATE | Google sheet URL
ZFNAMASS |  |  | ZFNAMASS | Google sheet URL

## Sheet5
AQPL Content error in AL11 file
/local/share/AEROSAP/FTP/DEM/I740/npi/o/TN_List.csv
qtml internal
MyQTML ID | Supplier ARPID | Supplier Name | Supplier Street | Supplier ZIP-code | Supplier City | Supplier Country | Supplier Approval | Captive/Independent | In-Situ/Ex-Situ | Facility Id | Facility Name | TMICD Reference | TM Reference | TM Title | TM Complexity | TM Family | TM surveillance sub family | Qualification Status | ATP Expiry Date | Qualification Limitations | Audit Performed Date | Industrial Qualification Reference | Industrial Qualification Type | Technical Qualification Required | Technical Qualification Date | Engineering Request Reference | Technical Qualification Reference | Technical Limitation | Deviation Required | Deviation Acceptance Date | Deviation Reference | Surveillance Date | Surveillance Reference | Surveillance Type | last on site | Next Surveillance Date | Nadcap Accredited | Nadcap Commodity | Nadcap Audit Checklist | External Cross Test Kit Reference | Year of Participation | RCA Reference | Tested Kit Reference | Final Status | Next External Cross Test Year | Request ID | Requestor Commodity | Qualification Need Date | Internal referent authorised for | Comments (internal) | Lead Qualified Auditor Siglum | Lead Qualified Auditor Name | Validator 1 Siglum | Validator 1 Name | Validator 2 Siglum | Validator 2 Name | Creation Line Date | First Industrial Qualification Date | Last Qualification Status Update Date | Last Update
QTML_ID | TEST_FAC_ARP_ID | SUPPLIER_NAME | SUPPLIER_STREET | SUPPLIER_ZIP_CODE | SUPPLIER_CITY | SUPPLIER_COUNTRY | SUPPLIER_APPROVAL | CAP_IND | INSITU_EXSITU | FACILITY_ID | FACILITY_NAME | TMICD_REF | TM_REF | TM_TITLE | TM_COMPLEXITY | TM_FAMILY | TM_SURV_SUB_FAMILY | QUALIF_STATUS_NAME | ATP_EXPIRY_DATE | QUALIF_LIMITATION | AUDIT_PERF_DATE | IND_QUAL_REF | IND_QUAL_TYPE | TECH_QUALIF_REQ | TECH_QUALIF_DATE | ENG_REQUEST_REF | TECH_QUALIF_REF | TECH_QUALIF_LIMIT | DEVIATION_REQUIR | DEVIATION_ACCEPT | DEVIATION_REFERE | SURV_DATE | SURVEILLANCE_REF | SURV_TYPE | LAST_ON_SITE | NEXT_SURV_DATE | NADCAP_ACCREDIT | NADCAP_COMMODITY | NADCAP_AUDIT_CHE | PTP_KIT_REF | PART_YEAR | RCA_REFERENCE | TESTED_KIT_REF | FINAL_STATUS | NXT_EXT_CR_TST_Y | REQUEST_ID | REQUESTOR_CMDTY | QUALIF_NEED_DATE | INTERNALREFLAB | COMMENTS | LEAD_QUA_AUDITOR | LQA_NAME | VALIDATOR_1_SIGLUM | VALIDATOR_1_NAME | VALIDATOR_2_SIGLUM | VALIDATOR_2_NAME | CREATED_DATE | FIRST_IND_QUALIF_DATE | LAST_QUA_STAT_UPDATE_DATE | LAST_UPDATE
______________________________
slg1 logs
NPI Request Reference | Created On | Created By | Request Type | Father STDP | Material | Description | Qualif | Standardization Status | Last Eng Decision Comment | Last Eng Date | Last Eng Actor | Procurement Status | Ordering Status | Need Date | Aircraft Type | Natco | Originator | Usage Group | Updated Flag | H Int Qty | H Int Date | Int Qty | Last Eng Decision | LDFOP | Last Proc Decision | Text | Last Proc. Date | Co Validation | ABC Code | HMG | ZMEABM_DESC | Int Date | Lead Time | Last Ord Decision | Last Ord Decision Comment | Last Ord. Date | Actor | Supplier Name | Supplier Code | Delivery Date | Updated Tool | Consuming Plant | MOD | MSN | One Shot | Old Material Reference
ZREQID | ZCREATE_DATE | ZCREATE_ID | ZREQTYP_DESC | ZSTDP | PART | PART_DESC | ZMAT_QUAL_NATCO | E_STATUS_T | E_DECISION_DESC | ZENGCHANGE_DATE | E_ACTOR | P_STATUS_T | O_STATUS_T | ZDEL | ZACTYP_DESC | ZCONSNATCO_DESC | ZORIGNATOR | ZUSAGEGRP | ZUPDATED | ZQTY_TOT | ZDEL_TOT | ZQTY_NATCO | E_DECISION_DESC | ZDEL_CORP | P_DECISION_DESC | P_COMMENT | P_UPDATE_DATE | ZCOVAL | ZVAL_CLASS | MATKL | ZMEABM_DESC | ZDEL_NATCO | ZQTY_CORP | O_DECISION_DESC | O_COMMENT | O_UPDATE_DATE | ZORDVAL_ID | ZLIFNR_TXT | LIFNR | ZTARGET | ZVALIDATOR_DESC | ZCONSPLANT_DESC | ZMOD | ZMSN | ZONE_SHOT | ZOLD_MAT_REF
NPI Request Reference | Created On | Created By | Request Type | Father STDP | Material | Description | Qualif | Standardization Status | Last Eng Decision Comment | Last Eng Date | Last Eng Actor | Procurement Status | Ordering Status | Need Date | Aircraft Type | Natco | Ori. | UG | Upd | H Int Qty | H Int Date | Int Qty | Last Eng Decision | LDFOP | Last Proc Decision | Last Proc Decision Comment | Last Proc. Date | Cov | ABC Code | HMG | Unit | Int Date | Lead Time | Last Ord Decision | Last Ord Decision Comment | Last Ord. Date | Actor | Supplier Name | Supplier Code | Delivery Date | Updated Tool | Consuming Plant | MOD | MSN | One Shot | Old Material Reference
ZREQID | ZCREATE_DATE | ZCREATE_ID | ZREQTYP_DESC | ZSTDP | PART | PART_DESC | ZMAT_QUAL_NATCO | E_STATUS_T | E_COMMENT | ZENGCHANGE_DATE | E_ACTOR | P_STATUS_T | O_STATUS_T | ZDEL | ZACTYP_DESC | ZCONSNATCO_DESC | ZORIGNATOR | ZUSAGEGRP | ZUPDATED | ZQTY_TOT | ZDEL_TOT | ZQTY_NATCO | E_DECISION_DESC | ZDEL_CORP | P_DECISION_DESC | P_COMMENT | P_UPDATE_DATE | ZCOVAL | ZVAL_CLASS | MATKL | ZMEABM_DESC | ZDEL_NATCO | ZQTY_CORP | O_DECISION_DESC | O_COMMENT | O_UPDATE_DATE | ZORDVAL_ID | ZLIFNR_TXT | LIFNR | ZLIFNR_DEL | ZVALIDATOR_DESC | ZCONSPLANT_DESC | ZMOD | ZMSN | ZONE_SHOT | ZOLD_MAT_REF
CSL_SIR
SIR ID | Service ID | Service Name | Service Category | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | Site ID | Site Name | Site City | Site Country | A/C Program | S Status | C Status | I Status | Commercial Site ARP ID | Commercial Site Name | WS ID | WS Reference | WS Name | Subtier / Service Provider | Comments | Attached Documents | SARF Validation Date | ATP expiry date | SARF Expiry Date | POA validation date | FOD validation date | SCQM-Login | SCQM-Name | SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Date of SIR Creation
SIR ID | TYPE ID | SERVICE NAME | CATEGORY NAME | ARP ID | SUPPLIER NAME | SUPPLIER CITY | SUPPLIER COUNTRY | SITE ID | SITE NAME | SITE CITY | SITE COUNTRY | PROGRAM FAMILY | S STATUS | C STATUS | I STATUS | COMMERCIAL SITE ARP ID | COMMERCIAL SITE NAME | WS ID | WS REFERENCE | WS NAME | SERVICE PROVIDER | COMMENT | DOCUMENT | SARF VALIDATION DATE | ATP EXPIRY DATE | SARF END DATE | POA VALIDATION DATE | FOD VALIDATION DATE | SCQM USER ID | SCQM NAME | SCQM SIGLUM | SIR CREATOR ID | SIR CREATOR NAME | SIR CREATOR SIGLUM | SIR CREATION DATE
SirID | TypeID | ServiceName | CategoryName | ArpID | SupplierName | SupplierCity | SupplierCountry | SiteID | SiteName | SiteCity | SiteCountry | ProgramFamily | SStatus | CStatus | IStatus | CommercialSiteId | CommercialSiteName | WsID | WsReference | WsName | ServiceProvider | Comment | Document | SarfStartDate | AtpExpiryDate | SarfEndDate | PoaValidationDate | FodValidationDate | ScqmID | ScqmName | ScqmSiglum | SirCreatorID | SirCreatorName | SirCreatorSiglum | SirCreationDate
ETSirSet
ZCL_Z_2T65_CSL_ODP_DPC_EXT
Z_CSL_GET_SIR_DETAILS
PO
SIR ID | Service ID | Service Name | Service Category | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | Site ID | Site Name | Site City | Site Country | A/C Program | S Status | C Status | I Status | Commercial Site ARP ID | Commercial Site Name | WS ID | WS Reference | WS Name | Subtier / Service Provider | Comments | Attached Documents | SARF Validation Date | ATP expiry date | SARF Expiry Date | POA validation date | FOD validation date | SCQM-Login | SCQM-Name | SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Date of SIR Creation
SIR ID | Service ID | Service Name | Service Category | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | Site ID | Site Name | Site City | Site Country | A/C Program | S Status | C Status | I Status | Commercial Site ARP ID | Commercial Site Name | WS ID | WS Reference | WS Name | Subtier / Service Provider | Comments | Attached Documents | SARF Validation Date | ATP expiry date | SARF Expiry Date | POA validation date | FOD validation date | SCQM-Login | SCQM-Name | SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Date of SIR Creation
PJ
SIR ID | Service ID | HMG | Service Category | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | Site ID | Site Name | Site City | Site Country | A/C Program | S Status | C Status | I Status | Commercial Site ARP ID | Commercial Site Name | WS ID | WS Reference | WS Name | Subtier / Service Provider | Comments | Attached Documents | SARF Validation Date | ATP expiry date | Qualification Date | POA validation date | FOD validation date | SCQM-Login | SCQM-Name | SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Date of SIR Creation
OLW
SIR ID | Service ID | Commodity | Service Category | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | Site ID | Site Name | Site City | Site Country | A/C Program | S Status | C Status | I Status | Commercial Site ARP ID | Commercial Site Name | WS ID | WS Reference | WS Name | Subtier / Service Provider | Comments | Attached Documents | SARF Validation Date | ATP expiry date | SARF Expiry Date | POA validation date | FOD validation date | SCQM-Login | SCQM-Name | SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Date of SIR Creation
CSL WS
WS ID | WS Reference | WS Name | WS Creation Date | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | WS Status | Nb of SIRs | Comment | Closed | WS SCQM-Login | WS SCQM-Name | WS SCQM-Siglum | Creator ID | Creator Name | Creator Siglum | Last Change date
WS ID | WS REF | WS NAME | CREATED DATE | ARP ID | SUPPLIER NAME | SUPPLIER CITY | SUPPLIER COUNTRY | WS STATUS | NB OF SIR | COMMENTS | CLOSED | SCQM ID | SCQM NAME | SCQM SIGLUM | CREATED USER | CREATOR NAME | CREATOR SIGLUM | UPDATED DATE
ETWsSet
ZCL_Z_2T65_CSL_ODP_DPC_EXT
Z_CSL_GET_WS_DETAILS
sServiceUrl = oResult.results[0].URL;
DFEK965260
MWS
ETWsLineSet | ZCL_Z_2T65_CSL_V3_ODP_DPC_EXT |  |  | ETWSLINESET_GET_ENTITYSET
WS ID | WS Reference | WS Issue | WS active flag | WS Name | WS Hierarchy | WS Family | S Provider ARP ID | S Provider Name | S Provider City | S Provider Country | S Provider Commercial ARP ID | S Provider Commercial Name | Service Family key | Service Family | HMG | Site ID | Site Name | A/C Program(s) | Serv Comp Status | WS Doc | QAP | DAN | ATS | Comp Matrix | Overall Progress | WS Creation Date | WS Creator Name | SCQM Name | Captain Name | myWS flag
Z_CSL_MANAGE_WS_LINE
CSL DIS
ETSirExportSet
SIR_ID | SRV_FAM_CODE | SRV_FAM | HMG | SRV_NAME | SRV_SUB_ACT_CODE | SRV_TYPE_DESC | PROCESS_FLOW | SITE | PROGRAMS | SIR_C_STATUS | SIR_I_STATUS | SIR_S_STATUS | COMMENTS | CRITICALITY | ACTIVE_AT_CC_LEVEL | DAYS_LEFT | FDA_REF | WS_ID | WS_REFERENCE | WS_ISSUE | WS_NAME | WS_HIERARCHY | WS_FAMILY | OVERALL_CRITIC | WS_COMP_STATUS | SRV_PROVIDER | SRV_PROVIDER_NAME | SRV_PROVIDER_CITY | SRV_PROVIDER_COUNTRY | SRV_PROVIDER_COMMERCIAL_ARP_ID | SRV_PROVIDER_COMMERCIAL_NAME | SRV_PROVIDER_COMMERCIAL_CITY | SRV_PROV_COMMERCIAL_COUNTRY | WS_REF_DOC | QAP_REF | DAN_REF | ATS_REF | COMPLIANCE_MATRIX | CREATED_DATE | CREATED_USER | WS_CREATOR_NAME | SCQM_ID | SCQM_NAME | SPECIAL_PROCESS | NOT_UPDATED | SITE_NAME
SIR ID | Service Family Code | Service Family Description | HMG Code | Service Activity | Service Sub-activity code | Service Sub-activity description | Process Flow | Special Process | Site ID | Site Name | A/C Program | SCQM status | SR status | SIR status | Comments | Criticality | SIR activation | Days left | FDA | WS ID | WS Reference | WS Issue | WS active flag | WS Name | WS Hierarchy | WS Family | Overall Criticality | Service Compliance Status | S Provider ARP ID | S Provider Name | S Provider City | S Provider Country | S Provider Commercial ARP ID | S Provider Commercial Name | S Provider Commercial City | S Provider Commercial Country | WS Doc | QAP | DAN | ATS | Comp Matrix | WS Creation Date | WS Creator ID | WS Creator Name | SCQM ID | SCQM Name
sir_id | srv_fam_code | srv_fam | hmg | srv_name | srv_sub_act_code | srv_type_desc | process_flow | special_process | site | site_name | programs | scqm_status | sr_status | sir_status | comment | criticality | sir_activation | days_left | fda | ws_id | ws_reference | ws_issue | ws_active_flag | ws_name | ws_hierarchy | ws_family | overall_criticality | srv_comp_status | s_provider_arp_id | s_provider_name | s_provider_city | s_provider_country | s_provider_comm_arp_id | s_provider_comm_name | s_provider_comm_city | s_provider_comm_country | ws_doc | qap | dan | ats | comp_matrix | ws_creation_date | ws_creator_ID | ws_creator_name | scqm_id | scqm_name
Z_CSL_SIR_EXTRACT
csl ssc
WS Reference | WS Issue | S Provider ID | S Provider Name | WS Creator ID | WS Creator Name | WS Creator Siglum | SCQM ID | SCQM Name | SCQM Siglum | Serv Comp Status | WS Document | QAP | DAN | ATS | Compliance Matrix | Site
ETWSSet
Z_CSL_WS_DETAILS
"/sap/opu/odata/SAP/Z_2F81_WPFIS_QIR_ODP_SRV/et_qirSet/?$format=GSheet&fname=myComp_qualif_export_31012025_161357&$filter=((I_supplier eq '0000071285' ))&$select=I_partno,I_matdesc,I_mpn,I_localmat,Qualif_scope,I_hmg,I_supplier,I_supname,I_supcity,I_supcoun,I_cfolder,I_msstate,I_estatus,I_qstatus,I_wstatus,I_pstatus,E_Inconsistency_Flag,I_certtype,I_criticality,I_scqm,I_cfolder,I_name,I_siglum,I_comments,IOrigin,Created_date,IUser,I_msn"
METHOD set_column_style_by_guid.
DATA: stylemapping TYPE zexcel_s_stylemapping.
IF me->excel IS NOT BOUND.
zcx_excel=>raise_text( 'Internal error - reference to ZCL_EXCEL not bound' ).
ENDIF.
TRY.
stylemapping = me->excel->get_style_to_guid( ip_style_guid ).
me->style_guid = stylemapping-guid.
CATCH zcx_excel .
EXIT. " leave as is in case of error
ENDTRY.
ENDMETHOD.
Airbus Normal Change: 151938, [Qualif] MS Decom - XFE
DFEK962652
DFEK962733
DFEK964946
Airbus Normal Change: 152048, [Qualif] MS Decom xEM
DEMK931402
DEMK931960
Airbus Normal Change: 154490, [myCSL] MS decom Topics
DFEK964607
DFEK965260
NSPI QFolder - Manage QIR
ZCL_Z_I740_MANAGE_QIR__DPC_EXT |  | ETLISTSET_GET_ENTITYSET |  | Z_NPI_GET_QIR_LISTS
Flag | Material | Material Description | Standard/Drawing | HMG | Supplier | ARP ID | E Status | Q Status | W Status | P Status | Incon Flag | C lev Cert type | Q Folder | SCQM-Login | SCQM-Name | SCQM-Siglum | Qualified Until | Manufacturer P/N | Usage Group | Usage Restriction | Created On | Created By | Last Changed On | Last Changed By | Withdrawal Comment
Deletion | Material | Material Description | Standard/Drawing | HMG | Supplier | ARP ID | E Status | Q Status | W Status | P Status | Incon Flag | Certificate Type | Q Folder | SCQM-Login | SCQM-Name | SCQM-Siglum | Qualified Until | Manufacturer P/N | Usage Group | Usage Restriction | Created On | Created By | Last Changed On | Last Changed By | Withdrawal Comment
EtListSet
sServiceUrl = oResult.results[0].URL;
Z_NPI_GET_QIR_LISTS
ETQirResultSet | Z_AQPL_QIR_RESULT_FILTER
AQPL - current records
Procurable | Qualified Until | Manufacture ArpId | Manufacture Name | Manufacture City | Manufacture Country | Manufacture Cage Code | Manufacturer Type | Standard | Airbus Material Id | Airbus Material Description | Manufacture Part Number | Harmonised Material Group | Interchangeability | Usage Restriction | P Status | P Status Description | P Status Last update | P5 Regulated Substance | Supplier Approved
Procurable | Qualified until | Manufacturer ARP ID | Manufacturer Name | Manufacturer City | Manufacturer Country | Manufacturer Cage Code | Material Type | Standard | Airbus Material ID | Airbus Material Description | Manufacturer P/N | HMG | Interchangeability | Usage Restriction | P Status | P Status Description | P Status Last Update | P5-Regulated Substances(only for blocked) | Supplier Approved
ETExportGermanSet | GE QPL | Z_AQPL_EXPORT_GERMAN
Manufacturer | Manufacturer Text | Location | Country | CAGE Co | Approval Status Text | Type of Data Text | Ident Number | Material | Airbus Material Text | Interchangeability Flag | Manufacturer PN | Usage Restriction Text | P Status | P Status Text | Change date Status P | Counter of QIR
Manufacturer | Manufacturer Text | Location | Country | CAGE Co | Approval Status Text | Type of Data Text | Ident Number | Material | Airbus Material Text | Interchangeability Flag | Manufacturer PN | Usage Restriction Text | P Status | P Status Text | Change date Status P | Counter of QIR
ETExportDeltaSet | uk fr | Z_AQPL_EXPORT_DELTA
Manufacturer ARP ID | Manufacturer Name | Manufacturer City | Manufacturer Country | Manufacturer Cage Code | Material Type | Standard | Airbus Material ID | Airbus Material Description | Interchangeability | Manufacturer PN | Usage Restriction | P Status | P Status Description | P Status last update
Manufacturer ARP ID | Manufacturer Name | Manufacturer City | Manufacturer Country | Manufacturer Cage Code | Material Type | Standard | Airbus Material ID | Airbus Material Description | Interchangeability | Manufacturer PN | Usage Restriction | P Status | P Status Description | P Status last update
ETExportTNSet | tn list | Z_AQPL_EXPORT_TN_LIST
LINE_NB | TN | SYSTEM_ID | SUB_SYSTEM_ID | COMPONENT_ID | LINE | REFERENCE | REFERENCE_TITLE | MATERIAL | NATCO | MATERIAL_SPECIFI | INDIV_PRODUCT_SP | MANUFACTURER_ARP | MANUFACTURER | PRODUCT_TYPE | PRODUCT_DESIGNAT | DRAWING_CODES | PROCESS_SPECIF | NOT_USED | IS_USED
LINE_NB | TN | SYSTEM_ID | SUB_SYSTEM_ID | COMPONENT_ID | LINE | REFERENCE | REFERENCE_TITLE | MATERIAL | NATCO | MATERIAL_SPECIFI | INDIV_PRODUCT_SP | MANUFACTURER_ARP | MANUFACTURER | PRODUCT_TYPE | PRODUCT_DESIGNAT | DRAWING_CODES | PROCESS_SPECIF | NOT_USED | IS_USED
AQPL - ICY
Valid | Update Date | SPEC from | STC from | SPEC to | STC to | ICY Code Designation | QIR(s)
Valid | Update Date | SPEC from | STC from | SPEC to | STC to | ICY Code Designation | QIR(s)
ETSearchInchSet |  | ICY_Export_ |  | CLEAR: lv_dd, lv_mm, lv_yyyy.
lv_dd = LS_REQLIST_INT_GSHEET-LAST_QUA_STAT_UPDATE_DATE+6(2).
Z_AQPL_INCHNBLTY_RESULT_FILTER |  |  |  | lv_mm = LS_REQLIST_INT_GSHEET-LAST_QUA_STAT_UPDATE_DATE+4(2).
lv_yyyy = LS_REQLIST_INT_GSHEET-LAST_QUA_STAT_UPDATE_DATE+0(4).
CONCATENATE lv_dd c_dot lv_mm c_dot lv_yyyy INTO LS_REQLIST_INT_GSHEET-LAST_QUA_STAT_UPDATE_DATE_DESC.
QTML MR
ETRequestShlpSet | MyQTML_exportrequest_ |  | Z_QTML_SEARCH_REQUEST |  | DFEK964946
Request ID | Request Creation Date | Requestor Name | Request Status | Request Type | Ex-Situ/In-Situ | MyQTML ID | TM Reference | TM title | TM complexity | Supplier ARP ID | Supplier Name | Supplier Street | Supplier City | Supplier ZIP-code | Supplier Country | Facility ID | Facility Name | TM Surveillance sub-family | Captive/Independent | TMICD | Reason For Need | Long_descript | Qualification Need Date | Comments on Request | Budget secured | Engineering Request Reference | Material/Process Specification Impacted | CNF Reference | TNF Reference | Current Supplier | A/C Progam(s) | Internal referent authorised for | Coordination Team | Requestor Login
Request ID | Request Creation Date | Requestor Name | Request Status | Request Type | Ex-Situ/In-Situ | MyQTML ID | TM Reference | TM title | TM complexity | Supplier ARP ID | Supplier Name | Supplier Street | Supplier City | Supplier ZIP-code | Supplier Country | Facility ID | Facility Name | TM Surveillance sub-family | Captive/Independent | TMICD | Reason For Need | Requestor Commodity | Qualification Need Date | Comments on Request | Budget secured | Engineering Request Reference | Material/Process Specification Impacted | CNF Reference | TNF Reference | Current Supplier | A/C Progam(s) | Internal referent authorised for | Coordination Team | Requestor Login
REQUEST_ID | CREATED_ON_DESC | CREATED_BY_NAME | STATUS_OF_REQ_DESC | REQUEST_TYPE | EXSITU_INSITU | QTML_ID | TM_REF | TM_TITLE | TM_COMPLEXITY | LIFNR | NAME1 | STRAS | ORT01 | PSTLZ | LAND1 | FACILITY_ID | FACILITY_NAME | TM_SURV_SUB_FAMILY | CAP_IND_DESC | TMICD_REF | REASON_FOR_NEED | LONG_DESCRIPT | QUALIF_NEED_DATE_DESC | COMMENTS_ON_REQU | BUDGET_SECURED | ENG_REF | LIST_PN | CNF_REF | TNF_REF | CUR_TST_FACILITY | AC_PROGRAMS_DESC | INTERNALREFLAB | COORDINATIONTEAM | CREATED_BY
QTML - MQ
ETQualifShlpSet | MyQTML_exportqualif_ |  | Z_QTML_SEARCH_QUALIFICATION |  | DFEK964946
TM Reference | Ex-Situ/In-Situ | MyQTML ID | Request ID | Qualification Validation Status | Supplier ARP ID | Supplier Name | Supplier Approval | TM_Family | TM_Sub_Family | TM_Surv_Sub_Family | IRR | Qualification Status | ATP Expiry Date | Next Surveillance Date | Nadcap Accredited | Nadcap Commodity | Nadcap Audit CheckList | Next External Cross Test Year | Kit Reference | Lead Qualified Auditor Name | Supplier City | Supplier Country | Captive/Independent | Facility ID | Facility Name | TMICD Reference | TM Title | TM Complexity | Internal referent authorised for | Qualification Limitations | LQA_siglum | Validator 1 Name | Validator 1 Siglum | Validator 2 Name | Validator 2 Siglum
TM Reference | Ex-Situ/In-Situ | MyQTML ID | Request ID | Qualification Validation Status | Supplier ARP ID | Supplier Name | Supplier Approval | TM Family | TM sub-family | TM Surveillance sub-family | IRR applicability | Qualification Status | ATP Expiry Date | Next Surveillance Date | Nadcap Accredited | Nadcap Commodity | Nadcap Audit CheckList | Next External Cross Test Year | Kit Reference | Lead Qualified Auditor Name | Supplier City | Supplier Country | Captive/Independent | Facility ID | Facility Name | TMICD Reference | TM Title | TM Complexity | Internal referent authorised for | Qualification Limitations | Lead Qualified Auditor Siglum | Validator 1 Name | Validator 1 Siglum | Validator 2 Name | Validator 2 Siglum
QSPL - REQ
ETReqFilterSet |  | MyQSPL_exportrequest_ |  | Z_QSPL_SEARCH_REQUEST | DFEK964946
Request ID | Request Creation Date | Requestor Name | Request Type | Request Status | Qualification Need Date | Requestor Commodity | Reason for Need | Ex-Situ/In-Situ | MyQSPL ID | Supplier ARP ID | Supplier Name | Supplier Country | Supplier City | PS Reference | PS Title | PI Reference | PI Title | Facility ID | Facility Name | PS Surveillance Sub Family | PNs/ Specifications | Coordination Team | Lead Qualified Auditor | Lead Qualified Auditor Name
Request ID | Request Creation Date | Requestor Name | Request Type | Request Status | Qualification Need Date | Requestor Commodity | Reason for Need | Ex-Situ/In-Situ | MyQSPL ID | Supplier ARP ID | Supplier Name | Supplier Country | Supplier City | PS Reference | PS Title | PI Reference | PI Title | Facility ID | Facility Name | PS Surveillance Sub Family | PNs/ Specifications | Coordination Team | Lead Qualified Auditor | Lead Qualified Auditor Name
QSPL - QUA |  |  |  |  | DFEK964946
ETSearchQualifSet |  | MyQSPL_export_ |  | Z_QSPL_SEARCH_QUALIFICATION
MyQSPL ID | Request ID | Validation Status | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | PS Reference | PS Title | PI Reference | PI Title | Facility ID | Facility Name | PS Family | PS sub-family | PS Surveillance Sub Family | Qualification Status | Supplier Approval | ATP Expiry Date | Next Surveillance Date | Qualification Limitations | Use Restricted | External Publication Authorised | Nadcap Accredited | Nadcap Commodity | Nadcap Audit Checklist | Industrial Qualification by Delegated Supplier | Surveillance by Delegated Supplier | Delegated supplier | Restricted Supplier | Couple Owner Siglum | Couple Owner Name | Lead Qualified Auditor Siglum | Lead Qualified Auditor Name | Comments | Validator Name | Updator ID
MyQSPL ID | Request ID | Validation Status | Supplier ARP ID | Supplier Name | Supplier City | Supplier Country | PS Reference | PS Title | PI Reference | PI Title | Facility ID | Facility Name | PS Family | PS sub-family | PS Surveillance Sub Family | Qualification Status | Supplier Approval | ATP Expiry Date | Next Surveillance Date | Qualification Limitations | Use Restricted | External Publication Authorised | Nadcap Accredited | Nadcap Commodity | Nadcap Audit Checklist | Industrial Qualification by Delegated Supplier | Surveillance by Delegated Supplier | Delegated supplier | Restricted Supplier | Couple Owner Siglum | Couple Owner Name | Lead Qualified Auditor Siglum | Lead Qualified Auditor Name | Comments | Validator Name | Updator ID
QTML GR
ETInternalReportSet |  | Z_QTML_QUALIFICATION_REPORTS |  | done | QTML_Internal_report_
ETExternalReportSet | /ind, cap | Z_QTML_QUALIFICATION_REPORTS |  |  | External_report_captive_
External_report_independent_
ETPTPKitReportSet |  | Z_QTML_PTP_KIT_REPORT |  | done | PTP_Kit_
captive
Supplier ARP ID | Supplier Name | Supplier Street | Supplier ZIP-code | Supplier City | Supplier Country | TM Reference | TM Title | TM Complexity | TM family | TM surveillance sub family | Qualification Status | ATP Expiry Date | InternalRefLab | In-Situ/Ex-Situ | Facility Id | Facility Name | Qualification Limitations
Supplier ARP ID | Supplier Name | Supplier Street | Supplier ZIP-code | Supplier City | Supplier Country | TM Reference | TM Title | TM Complexity | TM family | TM surveillance sub family | Qualification Status | ATP Expiry Date | Internal referent authorised for | In-Situ/Ex-Situ | Facility Id | Facility Name | Qualification Limitations
independent
Supplier ARP ID | Supplier Name | Supplier Street | Supplier ZIP-code | Supplier City | Supplier Country | TM Reference | TM Title | TM Complexity | TM family | TM surveillance sub family | Qualification Status | ATP Expiry Date | In-Situ/Ex-Situ | Facility Id | Facility Name | Qualification Limitations
Supplier ARP ID | Supplier Name | Supplier Street | Supplier ZIP-code | Supplier City | Supplier Country | TM Reference | TM Title | TM Complexity | TM family | TM surveillance sub family | Qualification Status | ATP Expiry Date | In-Situ/Ex-Situ | Facility Id | Facility Name | Qualification Limitations
QSPL GR
ETInternalReportSet | QSPL_INTERNAL |  | Z_QSPL_QUALIFICATION_REPORTS
MyQSPL Id | Request ID | Supplier ARPId | Supplier Name | Supplier street | Supplier city | Supplier ZIP-code | Supplier country | Supplier Approval | Specialist | PS reference | PS title | PS deletion flag | PI reference | PI title | PI deletion flag | Supplier PI reference | PS complexity | PS family | PS Surveillance sub-family | Qualification status | Qualification limitations | ATP Expiry date | in Situ / Ex Situ | Facility id | Facility name | External publication authorised | Audit Date | Industrial qualification reference | Industrial qualification type | Technical qualification required | Technical qualification date | Engineering request reference | Technical qualification reference | Technical limitation | Deviation required | Deviation acceptance date | Deviation reference | Last surveillance date | Next Surveillance Date | Surveillance reference | Surveillance type | Nadcap commodity | Nadcap Audit checklist | Nadcap Accredited | Industrial Qualification by Delegated supplier | Surveillance by Delegated supplier | Use Restricted | Restricted supplier ARPid | Restricted supplier name | Delegated supplier ARPid | Delegated supplier name | Comments (internal) | Couple Owner Siglum | Couple Owner Name | Qualification Auditor Siglum | Qualfication Auditor Name | Validator Siglum | Validator Name | Validator 2 Siglum | Validator 2 Name | Creation line date | First industrial qualification date | Last status update | Last Update
MyQSPL Id | Request ID | Supplier Name | Supplier street | Supplier ZIP-code | Supplier City | Supplier Country | Supplier Approval | Specialist | PS reference | PS title | PS deletion flag | PI reference | PI title | PI deletion flag | Supplier PI referenc | PS complexity | PS family | PS Surveillance sub- | Qualification status | Qualification limita | ATP Expiry date | in Situ / Ex Situ | Facility id | Facility name | External publication | Audit Date | Industrial qualifica | Industrial qualifica 1 | Technical qualificat | Technical qualificat 1 | Engineering request | Technical qualificat 2 | Technical limitation | Deviation required | Deviation acceptance | Deviation reference | Last surveillance da | Next Surveillance Da | Surveillance referen | Surveillance type | Nadcap commodity | Nadcap Audit checkli | Nadcap Accredited | Industrial Qualifica 2 | Surveillance by Dele | Use Restricted | Restricted supplier | Restricted supplier 1 | Delegated supplier A | Delegated supplier n | Comments (internal) | Couple Owner Siglum | Couple Owner Name | Qualification Audito | Qualfication Auditor | Validator Siglum | Validator Name | Validator 2 Siglum | Validator 2 Name | Creation line date | First industrial qua | Last status update | Last Update
ETLQAReportSet | MyQSPL_LqaDashboard_ |  | Z_QSPL_LQA_DASHBOARD
ETExternalReportSet |  |  | Z_QSPL_QUALIFICATION_REPORTS |  |  | EXTERNAL_EX_ |  | EXTERNAL_IN_
External exsitu
Supplier ARPId | Supplier Name | Supplier street | Supplier city | Supplier ZIP-code | Supplier country | Supplier Specialist | PS reference | PS title | PI reference | PI title | Qualification status | Qualification limitations | ATP Expiry date | PS family | PS Surveillance sub-family
Supplier ARPId | Supplier Name | Supplier street | Supplier city | Supplier ZIP-code | Supplier country | Supplier Specialist | PS reference | PS title | PI reference | PI title | Qualification status | Qualification limitations | ATP Expiry date | PS family | PS Surveillance sub-family
External Insitu
Supplier ARPId | Supplier Name | Supplier street | Supplier city | Supplier ZIP-code | Supplier country | PS reference | PS title | PI reference | PI title | Qualification status | Qualification limitations | ATP Expiry date | Facility id | Facility name | PS family | PS Surveillance sub-family
Supplier ARPId | Supplier Name | Supplier street | Supplier city | Supplier ZIP-code | Supplier country | PS reference | PS title | PI reference | PI title | Qualification status | Qualification limitations | ATP Expiry date | Facility id | Facility name | PS family | PS Surveillance sub-family
if ((oData.N_ETRequestInp_ETRequestList.results[j].ZREQTYP === "30") ¦¦ (oData.N_ETRequestInp_ETRequestList.results[j].ZREQTYP ===
90)) {
oData.N_ETRequestInp_ETRequestList.results[j].ZSTDP = "";
}
Z_2T65_CSL_SIR Z_2T65_CSL_ODP SRV Z_CSL_GET_SIR_DETAILS
myCSL OLW |  | date format incorrect m/dd/yyy, instead fo dd.mm.yyyy | 2025-12-02
SARF_START_DATE
SARF_END_DATE
SIR_COMP_EXP_DT
SIR_CREATION_DATE
ATP_EXPIRY_DATE
POA_VALID_DATE
FOD_VALID_DATE

## Business feedback
Found by | Application | Issue # | issue | date | Dxx | Ixx | Qxx | Fixed | Comments | https://docs.google.com/spreadsheets/d/1M38Hb46jiDJ_rtShdVrVCPsS9Ofrh0qDVkudezpR2ec/edit?gid=573172672#gid=573172672
Isabell D. | NSPI Request - Manage material | 1 | Last proc date comment column labelled "text" | 28/01/2025 |  | Y |  | Y
Isabell D. | NSPI Request - Manage material | 2 | Last proc date not displayed | 28/01/2025 |  | Y |  | Y
Isabell D. | NSPI Request - Manage material | 3 | Unit column labelled "ZMEABM_DESC" | 28/01/2025 |  | Y |  | Y
Isabell D. | NSPI Request - Manage material | 4 | Last Order date not displayed | 28/01/2025 |  | Y |  | Y
Isabell D. | NSPI Request - Manage material | 5 | Qualif column displayed as "X/<Blank>" instead of "Yes/No" | 28/01/2025 |  | Y |  | Y | Single char field in ABAP, working on workaround to fix
Isabell D. | NSPI Request - Manage material | 6 | Cov column displayed as "X/<Blank>" instead of "Yes/No" | 28/01/2025 |  | Y |  | Y | Single char field in ABAP, working on workaround to fix
Isabell D. | NSPI Request - Manage material | 7 | Button Export still visible for role Engineering, Ordering, Procurement. |  |  | Y |  | Y
G.B | NSPI Request - Manage material | 8 | Layout not harmonized | 28/01/2025 |  |  |  | N | Need the exact changes which are expecting in layout
G.B | NSPI QFolder - Manage QIR | 1 | Certificate Type not displayed | 28/01/2025 |  | Y | Y | Y
G.B | myCSL - Manage SIR (OLW) | 1 | Service ID column not correclty labelled | 28/01/2025 |  |  |  | Y
G.B | myCSL - Manage SIR (OLW) | 2 | Commodity Column not correctly labelled | 28/01/2025 |  |  |  | Y
G.B | myCSL - Manage SIR (OLW) | 3 | Document field displays X/<Blank> instead of Yes/No | 28/01/2025 |  |  |  | Y
G.B | myCSL all applications | 4 | Doc ref empty instead of "No Document" | 28/01/2025 |  |  |  | Y | SIR, WS, mws, dis, ssc
Anais M | NSPI QFolder - Manage QIR AQPL - Qualified Part List AQPL - Interchangeability myCSL - Manage Works Specification Line myCSL - Display SIR myCSL - Search Service & Contact myQSPL - Request (browser in French) myQSL - Qualification (browser in French) myQSPL - report (browser in French) myQTML - Request (browser in French) myQTML - Qualification (browser in French) myQTML - report (browser in French) | 1 | Columns labelled with field names nspi-qfolder, aqpl-qpl, icy, csl,qspl, qtml | 31/01/2025 |  |  | Y | Y | test file link : https://docs.google.com/spreadsheets/d/1M38Hb46jiDJ_rtShdVrVCPsS9Ofrh0qDVkudezpR2ec/edit?gid=573172672#gid=573172672
Anais M | NSPI QFolder - Manage QIR myCOMP - Manage QIR myCOMP - Manage CFolder AQPL - Qualified Part List AQPL - Interchangeability myCSL - Manage Works Specification Line myCSL - Display SIR myQSPL - Request (browser in French) myQSL - Qualification (browser in French) myQSPL - report (browser in French) myQTML - Request (browser in French) myQTML - Qualification (browser in French) myQTML - report (browser in French) | 2 | Filter does not work | 31/01/2025 |  |  |  | . | Not supporting offline filters
Anais M | <Need actual application names - where we have the issue> | 3 | xFeld field are displayed X/<Blank>, instead of yes/no or True/False | 31/01/2025
Anais M | NSPI QFolder - Manage QIR AQPL - Qualified Part List AQPL - Interchangeability myCSL - Manage Works Specification Line myCSL - Display SIR myCSL - Search Service & Contact myQSPL - Request (browser in French) myQSL - Qualification (browser in French) myQSPL - report (browser in French) myQTML - Request (browser in French) myQTML - Qualification (browser in French) myQTML - report (browser in French) | 4 | Sort order in the screen is the order in the GSheet | 31/01/2025 |  |  |  | N | Not supporting offline sort
Anais M | AQPL - Airbus Qualified part list | 1 | "P5 regulated subtance" column not displayed | 31/01/2025 | y |  | Y | Y | Need test data where P5 regulated substance value exists. Column is available in gsheet. --> material ABS1133D025 in Qxx
Anais M | AQPL - Interchangeability | 2 | Update date format (expected format is dd.mm.yyyy) | 31/01/2025 | KO (date = dd.mm.yy) 12/02/25 : Ok ! |  | Ko | Y | As discussed, Need confirmation on the date format to display in gsheet.
Anais M | myCSL - Manage WS line | 1 | XML error message. The field "Overall Progress" is not defined in the WS line entityset in QFx | 31/01/2025 | Y | Y |  | Y | Available in Ixx
Anais M | myCSL - Manage SIR OLW | 1 | credential requested | 31/01/2025 | Y |  |  |  | Please test once in Integration system as i dont see this with my user id.
Isabell D. | NSPI QFolder - Manage QIR |  | Deletion flag display is "X/<Blank>" instead of "True/False" | 2025-04-02 | Y |  | Y | Y | Done
Anais M | AQPL - Airbus Qualified part list |  | P status las update wrong values (Complete in Excel, '0' in Gsheet) | 2025-04-02 | Y |  | Y | Y | Done
G.B | NSPI QFolder - Manage QIR |  | Date in the file shoud be yyyymmdd | ` | Y | ` | Y | Y | Done
| NSPI Request - Manage material |  | Date in the file shoud be yyyy-mm-ddThh-mm-ssZ |  | Y |  |  | Y | Done | 2021-09-30T00:00:00Z
G.B | NSPI Request - Manage material |  | Field "father Standard Part" is filled in the GSheet even if there is no value in the list. (NPI0094398 in QEM) | 2025-11-02 | Y |  |  | Y | Done
GB | AQPL - GE QPL |  | Date change P status = 12/29/0000 (empty in Excel) | 2025-11-02 | Y |  |  | Y | 0' in both xlsx and gsheet | /local/share/AEROSAP/FTP/DEM/I740/npi/o/German_QPL.csv
GB | AQPL - FR,SP,UK QPL |  | P Status last update = 12/30/000 (Complete in Excel) | 2025-11-02 | Y |  |  | Y | "Complete" in both xlsx and gsheet | /local/share/AEROSAP/FTP/DEM/I740/npi/o/1_ FR-UK-SP QPL - QIRs in P2 & P3.csv
GB | myCSL OLW |  | date format incorrect m/dd/yyy, instead fo dd.mm.yyyy | 2025-12-02 | Y |  |  | Y | Done

## myCSL - Manage SIR (OLW)
Issue #1
Excel
GSheet

## NSPI Request screenshot
Issue #1
Excel
GSheet
Issue #2
Issue #3
Excel
Gsheet
Issue #4
Issue #5
Excel
Fixed
GSheet
Issue #7